# Project Plan: 360Giving Publishing

[Publisher name]

Key: [[Guidance from 360Giving]] ; 
[prompts to be filled in/overwritten/deleted as appropriate]

# Introduction

[[This publishing project plan template is a practical resource designed to help you plan and execute the project of publishing grants data using 360Giving Data Standard.

It is aimed at first-time publishers, particularly larger organisations that need to coordinate resources across multiple people or teams.

Drawing on 360Giving’s experience supporting hundreds of publishers, this template is structured to include the key steps and considerations, and prefilled wherever possible.

To use this template, please ‘fill in the blanks’ by overwriting the prompts highlighted in orange and enclosed in square brackets. These indicate areas where you need to input specific information relevant to your organisation. Please feel free to customise it to fit your needs by removing or adding sections, and adapt any wording. This template is a starting point, intended to be a flexible tool you can make your own.]]

## Description

This is the project plan for [publisher name] to publish our grants data using the 360Giving Data Standard for the first time.

360Giving is a charity that supports funders to publish their grants data, and helps people to use that data to improve charitable giving. The 360Giving Data Standard allows grantmakers to share their grants data openly, in a standardised format. This means it can be easily analysed with data from other organisations – so that people can understand the funding context, make informed decisions, and collaborate.

Once published, our data will appear in GrantNav, 360Giving's free search engine for grants data. People can use GrantNav to search, filter and download data about awarded grants supporting good causes and communities across the UK.

## Background

[Give any background, for example, what prompted our organisation to decide to publish, why now, including whether we have made a pledge previously or as part of a collaboration]

# Purpose

## Goal(s)/objectives for [publisher name]

- [Add at least one objective here – go to 360Giving’s Why Publish page for inspiration]

- …

## Aims for [publisher name]

[Add what results we expect from doing this project, for example:

- Pages in GrantNav and GrantVis, and the Grants to Individuals Dashboard [if we make grants to individuals and families], showcasing our data

- Page on Data Quality Dashboard for our files and summary of our data quality

- Ability to have analysis of our grantees in common with other funders – and understand who else funds our grantees]

## Outcomes

[Describe outcomes for ourselves and prospective users of our data (which could be our grantees, grant seekers, other grantmakers, researchers and policy makers)]

- [Add around two or three outcomes here – for example appearing in GrantNav raises our grantee’s profile, shows they have other sources of income and have passed our due diligence, increasing their chances of being funded by others; availability of our data alongside others in a standardised format increases efficiency of reporting and analysis to support informed strategy development]

- …

## Outputs

- One or more files of published data about our grants which complies with the 360Giving Data Standard (360Giving data).

- A page on our website which hosts the 360Giving data file(s), open licence and links to our data in GrantNav, and if we opt in, displays a GrantNav widget which embeds our data on the page.

- Documentation of our process and decisions to make it easier to publish next time, and facilitate handing over responsibility for this task internally if needed.

- [Add any other outputs we want to develop as part of the process, for example the addition of new fields on our grant application form or new data collection steps in our processes]

# Delivery

## Approach

In order to publish our grants data using the 360Giving Data Standard for the first time, we will follow the approach in the step-by-step guidance for publishers provided by 360Giving. This is summarised below:

### Plan – know what we need

First, we need to plan our process so that we understand what's involved, who's involved (including who signs off), and when it will happen. Creating a sufficiently detailed plan in advance allows us to coordinate and get organisational buy-in to ensure we have secured the time commitment and resources we will need from the right people at the right time. Recording our process and progress throughout the project will allow us to publish more quickly and efficiently next time we want to update our grants data.

### Prepare – get it ready

In order to prepare our data for publishing, we need to make some key decisions about what data we want to publish (meaning which records and fields) and understand what work we need to do to our data (for example, clean up, extract from our system and refine). [Add or remove details as required. This may involve coordinating with external suppliers/consultants, for example, grantmaking database providers, or with specialist data colleagues/teams.] We also need to establish a robust way of managing privacy/data protection, and ensure the data we share is high quality, meaning it tells an accurate story about our grantmaking, and is useful for us and others.

### Publish – share our data

Once we've prepared the data, we need to ensure that it is checked, signed off, and ready to publish. We can then publish and maintain it on our website, alongside an open licence that states anyone can use it. [Add or remove details as required e.g. This may involve coordinating with specialist communications colleagues/teams.] We need to let 360Giving know we’ve done this by submitting the link(s) to our file(s) so that the data can appear in GrantNav, and providing them with some supplementary information, including our logo, so it can appear alongside our files.

### Post Publishing – promote and resolve

After publishing, we should promote our data both internally and externally to ensure we get  the benefits from the work we’ve done to prepare and publish our grants data. [Add or remove details as required, e.g. We will be able to explore our own data in 360Giving’s tools, like GrantNav, and look at it alongside our peers’ data. We will add a widget to our website which embeds our data and showcases it to applicants/others. We will use the new insights and visualisations in our marketing communications and/or board papers.]

We also need to make sure that we have a process for addressing any issues that might come up about our published data (making a correction or taking it down), and that 360Giving are able to reach us if they are contacted about an issue with our data.

### Republishing and updating – regularly publish again

We don't just want to publish our past grants as a one-off, but to continue sharing new grants regularly. Publishing for the first time is a project, but it should be easier to publish again once we've done it before. We will also carry out an evaluation to learn how we can make republishing easier. Then, we will agree how frequently we will republish our data and incorporate it into our regular plans, aiming to add new grants information [delete as applicable: shortly after as we award them/on a monthly basis/on a quarterly basis/once every six months/at least once a year].

## Schedule

[Add or delete as appropriate]

| When | How | Who |
| --- | --- | --- |
| [Range or due date] | Create a plan and/or business case and get it approved | [Role/person] |
|  | Register with the 360Giving Helpdesk |  |
|  | Make key decisions about what data to publish, including what timeframe. |  |
|  | Extract and prepare the data, including checking for personal or sensitive information inadvertently in the extracts, correcting errors, collecting new data if needed, and adding or updating fields on application forms and/or in our database, for example, adding format validation and lookups We will do this by [delete as appropriate: Exporting our source report and converting it manually / Exporting a 360Giving-formatted report, based on a built-in conversion report/process / Creating a direct feed from our system, with no manual manipulation, and updates triggered by status] |  |
|  | Carry out data quality and data protection checks, including using 360Giving's Data Quality Checker to test the file(s) |  |
|  | Make key decisions about hosting the data, including where to host it and what licence to use |  |
|  | Sign off the data |  |
|  | Create a communication plan |  |
|  | Set up the data hosting page, including the open licence statement, and upload the data to the website |  |
|  | Go live! Publish the data and let 360Giving know using their Data Submission Form |  |
|  | Decide what frequency to publish, incorporate republishing into our plans and make sure the whole process is documented for next time |  |
|  | Celebrate our data and execute our communications plan |  |
|  | Explore our data and make a plan for how we will use it going forward |  |
|  | Evaluate the project, document our learning, update our process documentation and continue to monitor the use and usefulness of our data |  |

## Scope

[Explain what is included/excluded from the project, and how it relates to other projects.]

For the scope of the data to be published, see our 360Giving Publisher Logbook which will help us document our decisions about the date range and any other criteria for which grants to publish and which fields we will include.

## Dependencies

[Identify any critical paths or needs from other projects, particularly relating to our policies, grant management system and website]

## Accessibility, inclusion and values

[Identify accessibility and inclusion considerations and how we will prioritise needs or how to build in our values.]

## External comms and engagement plans and needs

[Describe what is needed from who/when – go to 360Giving’s Share the news page for inspiration, including a communications pack for publishers]

# Project Governance

## Responsibilities

[Review 360Giving’s guidance on Roles in the publishing process and allocate them within your organisation. Roles can be added or merged, and the responsibilities divided differently if needed.]

| Role | Responsibilities | Named person |
| --- | --- | --- |
| [Role 1] | - [Responsibility A] - [Responsibility B] |  |
| [Role 2] | - … |  |

## Risk management

[Add or delete as appropriate]

| Risk | Mitigation |
| --- | --- |
| Preparing and publishing the data falls off the priorities with other work. | - Clear roles and responsibilities for preparing and publishing the data are agreed and proportionate to the task. - Proper planning to identify dependencies and workload challenges in advance |
| Out-of-date or incorrect information is published | - All data will be checked by a staff member with appropriate knowledge of the grants, either before or after it is extracted from the grants management system. |
| Personal and/or sensitive information is disclosed during the publishing process | - Assess risk for each field to include personally identifiable information as part of deciding what information to publish - If a risk is identified, put in place appropriate mitigations e.g. exclude, redact, anonymise or make generic. - Review the data for personally identifiable information before publishing. |
| Grantees are unaware/unhappy that information about their project has been published | - Make grantees aware that we plan to publish and explain what we will publish and why, with sufficient time (at least one month) to ask questions or raise concerns |
| [If you need to collect more information in order to publish] Additional information requested is considered burdensome or intrusive for grant recipients | - Assess the burden on grant recipients as part of the application process. - Clearly explain the rationale for why we are requesting the information (including potential benefits for grant recipients and their users/participants) |
| [Any other risks identified] | [Add mitigations] |

## Financials

[Add or delete as appropriate]

| Supplier | Deliverable(s) | Cost |
| --- | --- | --- |
| [Name of supplier e.g. Grant Management System provider] | [What they will deliver e.g. new fields in the grant application form and database, a way of extracting a compliant report, data validation] | [Add budgeted/ quoted cost] |
| [Name 2] | [Deliverable 2] | [Cost 2] |
| Total |  |  |

[If relevant, procurement process/approach - as per our procurement policy]

## Monitoring & evaluation

[How the project of publishing for the first time will be evaluated and measured/monitoring mechanisms.]

[[When you are ready to carry out the evaluation, give each row a score, e.g. numerical or Red/Amber/Yellow/Green, and document any learning or recommendations for the next time you publish your data.]]

### Objectives and outcomes

[Add each of the objectives and outcomes listed above to the table and describe how you will measure whether it was achieved]

| Category | Outcome | Measure(s) | RAYG/ score |
| --- | --- | --- | --- |

### Outputs/deliverables

[Add any additional outputs or deliverables, and describe how you will measure whether each one was achieved]

| Category | Output | Measure(s) | RAYG/ score |
| --- | --- | --- | --- |
| Our published data | We have produced data which complies with the 360Giving Data Standard. | Data passes the Data Quality Checker. |  |
| Our published data | No significant errors or data breaches were identified after publishing. |  |  |
| Our published data | The data accurately tells the story of our grantmaking priorities. |  |  |
| Our published data | The data is useful and usable by us and others, allowing us to better understand our grantmaking by showing how we fit in the overall picture, and enabling us to make strategic decisions about our grantmaking. | Measures include: data earns the majority of available Data Quality Dashboard badges; data can be used to produce meaningful insights such as a ‘Who funds with who’ report. |  |
| Data hosting & presentation | We have shared our data in an accessible and compliant way. | Measures include: we have signposted and showcased our data on our website; we receive [X] visits to our data hosting page per month. |  |
| Documentation | We have documented our process; the documentation is comprehensive, clear and user friendly; the documentation is accessible and easy to find. |  |  |

### Process

[Add any areas of process you wish to evaluate, describe how you will measure whether each one was achieved]

| Category | Aim | Measure(s) | RAYG/ score |
| --- | --- | --- | --- |
| Project management | Good project management. | The project was on time. |  |
| Finances | Sound allocation of resources. | The project was within budget. |  |
| Governance | Clear governance. | Appropriate use of processes and platforms, clear roles and sign off were established. |  |
| Data protection compliance | Compliant data protection process and practices. | We followed our existing data protection and/or privacy policies, or we updated our data protection and/or privacy policies following an appropriate process. |  |
| User/grantee engagement | Proper consideration for user needs. |  |  |
| Stakeholder engagement | Proper stakeholder engagement. |  |  |
| Quality assurance | Appropriate testing. |  |  |
| Comms | Engaging and high quality external comms to support launch. |  |  |
| Wellbeing | Staff were comfortable during the project and not unduly stressed. |  |  |

### Recommendations and learning

[Complete after evaluation.]

# Appendices

[Add links to any supporting documentation identified in planning or throughout the project, e.g. a brief for developing our grant management system, previous analysis of the data, our publisher logbook, draft files of data]

Publisher Guidance | Get support | Data Quality Checker | Data Submission Form